## Meeting Protocol
| Document under review |  |  | System Requirements Specification
| Document version |  |  | v0.9
| Date |  |  | 2011-11-15
|  |  | Moderator and scribe | Markus Borg (RISE Research Institutes of Sweden)
| Reviewers |  |  | P1=Thanh Bui (RISE Research Institutes of Sweden), P2=Piotr Tomaszerski (RISE Research Institutes of Sweden)
P3=Olof Lennartsson (Infotiv), P4=Elias Sonnsjö (Infotiv)
P5=Sebastian Brink (Combitech), P6=Emelie Folkesson (Combitech)
For each issue, a '1' in columns H-M indicates than an independent reviewer (P1-P6) identified it.
| Checklist |  |  | ETSA03 SRS Review Checklist
| 47 |  | Issues found |  | 159 | Estimated issues left |  |  | 22.82% | Group yield
|  |  | Individual yield |  |  | 6.311% | 9.223% | 6.311% | 4.854% | 0.9709% | 0.9709%
ID | Pos in SRS | Issue ID in checklist | Description |  | Accept/Reject | P1 | P2 | P3 | P4 | P5 | P6 | U | C | F | Changes made/comments | Link to commit
1 | Figures | 2 | Figures and tables do not have captions (incl. numbers). |  | Accept | [6 empty] | 0 | 1 | 1 | Added captions. | 1ccb44aeee805db6643f70b70142118b918d503c | bar: P1; P3 to P6
2 | General |  | Somewhere early in the document specify that this spec will have parts that are providing informational background and not the actual requirements (like the references, and those parts with grey line on side in section 4) |  | Accept | [6 empty] | 1 | 0 | 1 | Explained that this document follows standard IEEE practice for SRS. Clarified how the quote environment in this SRS. | afa932ee5e7c8c136e017cf671eb425c55400e77 | bar: P2
3 | 1.6 |  | Double-check that all references are found in the running text. |  | Accept | [6 empty] | 1 | 0 | 1 | Removed four references. | a67b9f25795e647d431e47e4e935203d7e4a9412 | bar: P3
4 | 1 |  | Fix possible contradiction: ESI Pro-SiVIC is not really in line with open science. |  | Accept | [6 empty] | 1 | 0 | 1 | Rephrased the sentence about open science. | 0553e323701e1ab16a806b574540cce12da75375 | bar: P3
5 | 1.1 |  | SAE is not listed in the glossary |  | Acceot | [6 empty] | 0 | 1 | 1 | Added SAE to the glossary. | 29a9f952d42f41c3e669c2d7eaf15ed14c112230 | bar: P3 to P4
6 | 1.2 |  | Too many academic references for a requirements specification? Motivate why we provide so many references in the document conventions. |  | Accept | [6 empty] | 1 | 0 | 1 | Elaborated on the concious choice of building SMIRK on peer-reviewed publications. | b3770b2295f3d444e542b011e9e9af736ec80fac | bar: P2
7 | 1.2 |  | Add hyperlink to AMLAS. |  | Accept | [6 empty] | 1 | 0 | 1 | Added a link in Sec 1.2. | 8ed71341dad5de76d2ff8c0c5e41e27219f9decf | bar: P2
8 | 1.2 |  | AMLAS is not a standard, thus replace mandate by recommend. |  | Accept | [6 empty] | 1 | 0 | 1 | Replaced mandate by prescribe. | 35a65d588430cb6c0cdda1c33ea47347e94504de | bar: P1
9 | 1.4 |  | Add researchers as another type of stakeholder. |  | Accept | [6 empty] | 1 | 0 | 1 | Researchers added. The section was restructured for clarity. | fdc0f1a9c02861b78556b857e79efe8d59dbd2fa | bar: P1
10 | 1.4 |  | Broaden the scope of the testers. Distinguish between different types of testers. What about independent testers? |  | Accept | [6 empty] | 0 | 1 | 1 | Split into two types of testers. Also specified developers as software developers. | 7ed994a1e1f23323219bac05c4b11eee503e49c3 | bar: P3 to P4
11 | 1.5 |  | Prioritize quality attrbutes: maintainability, interpretability, portability etc. What do we care about? What are the main quality drivers that motivate design choices? |  | Accept | [6 empty] | 1 | 0 | 1 | Elaborated on how we prioritize quality characteristics. | 31ebdcd334da5577bbaa340094471d0459552eb4 | bar: P3
12 | 1.5 |  | What does sharing effectively mean? Can it be so that camera is not available at the moment because something else is using it? It is a bit confusing on how this information affects the requirements. Clarify the section. |  | Accept | [6 empty] | 0 | 1 | 1 | Clarified that we do not consider any shared resources in the MVP. | 0b961095cbef71bb33881396731b304f020050f4 | bar: P2; P4
13 | 1.6 |  | Indicate that the SAD is for SMIRK |  | Accept | [6 empty] | 1 | 0 | 1 | Added structure to the reference list. Also added missing DMS. | 02106dfb287374d9c58798ac21a3e8477047159a | bar: P1
14 | 1.6 |  | ADAS not in the glossary |  | Accept | [6 empty] | 1 | 0 | 1 | Added ADAS to the glossary. | f7c368a01d057b1778bd1b5aabdf229bb644aea8 | bar: P5
15 | 1.6 |  | Clarify how the how the references affect the requirements specification. |  | Accept | [6 empty] | 0 | 1 | 1 | Clarified how we use external references. | 0355f66460f913d53f6ceba6aa0bea203a8c5b73 | bar: P2 to P3
16 | 1 |  | MVP is a research prototype that provides PAEB that adheres to development practices mandated by the candidate standard ISO 21448. Clarify that the integrated OSS assets do not adhere to the standard? |  | Partial accept | [6 empty] | 1 | 0 | 1 | Added explicit product and project goals. The clarification about OSS assets was added to the overal SMIRK README. | fcb6ff421a211072a6ee22ad0c5f7c5f1d50bb6b | bar: P2
17 | 1.6 |  | PeVi cannot be found in the Ben Abdessalem et al., (2018) Change the reference. |  | Accept | [6 empty] | 1 | 0 | 1 | Replaced the reference with the authors' prior work. | 8cb493ea3d710d77142fe3fe08e2e66ca185eef5 | bar: P2
18 | 1.6 |  | Clearly state what aspect of industrial relevance we are after in this particular work. A significant amount of safety-critical standards stress not only the testing part but also they set requirements on the working/development process, the technologies used etc. |  | Reject | [6 empty] | 1 | 0 | 1 | No change to SRS. Related to comment 16. Clarified in the README that the SMIRK focuses on the novel aspects introduced by ML. | cec8f8ee810014a23794cf9ada44493e7fd52979 | bar: P2
19 | 2.1 |  | Add some negative example where the car shall not break. A ghost? Also number the the scanarios. |  | Accept | [6 empty] | 0 | 1 | 1 | Added a ghost example. All scenarios were numbered in relation to comment 1. | d7c4760b1ea44c18246e15242d74cb36cf104a78 | bar: P3 to P4
20 | 2.1 | 4 | Clarification: Are the 5 scenarios the requirement scope or only example. Clarify that they are examples. |  | Accept | [6 empty] | 1 | 0 | 1 | Clarified in the text. | b6379f7f5a90309a236dd1c21f97edbaebc0117b | bar: P1
21 | 2.1 | 6 | Clarification: If brakes can be manipulated also by other ADAS functions, add a separate box before brake. |  | Reject | [6 empty] | 1 | 0 | 1 | The same argument could be made for all actuators and would make the figure hard to read. We assume there is brake management in the Brakes box. | bar: P1
22 | 2.1 |  | Describe variation points (possible initial placement + possible angle of movement + speed range) rather than having pictures |  | Reject | [6 empty] | 1 | 0 | 1 | The figures are supposed to demonstrate the function, not provide a comprehensive definition of parameters and ranges. The ODD covers ranges. | bar: P2
23 | 2.1 |  | Unclear how SMIRK coexists with other systems (ahderance to some higher level architecture, resource consumption limitation or alike, resource sharing rules for the actuators & sensors). |  | Accept | [6 empty] | 1 | 0 | 1 | Clarified the simplistic nature of the SMIRK MVP as an isolated ADAS. | ca0a251a391ca82b1cf3c32918810a2de1947351 | bar: P2
24 | 2.2 |  | Contradiction: According to the image above SMIRK is a component that uses other components. Here the radar and camera are descibred as parts of SMIRK. |  | Accept | [6 empty] | 1 | 0 | 1 | Removed the contradiction. | 6b16500f489c6a4b910873d6128e8823aeccde1d | bar: P2
25 | 2.2 |  | Add seconds to the TTC. |  | Accept | [6 empty] | 1 | 0 | 1 | Added the threshold. | b2ae2dbb34ed78c921a55f47882eef1c70a935ae | bar: P4
26 | 2.2 |  | Clarify that the sensor-algorithm-actuator split originates in ISO 21448. |  | Reject | [6 empty] | 1 | 0 | 1 | ISO 21448 moved to beginning of sentence based on comment 24. | bar: P4
27 | 2.3 |  | Add versions and description of API and Prosivic version and Python. |  | Partial accept | [6 empty] | 0 | 1 | 1 | Added the Pro-SiVIC version, the API follows suit. Python version to be added in the overall README. | 35fcfe95e4744277b83447398eb2097892733b72 | bar: P1; P3
28 | 2.3 |  | TCP is not explained. Add to glossary. |  | Accept | [6 empty] | 1 | 0 | 1 | Added to the glossary along with API in the same sentence. Acronyms not spelled out in the running text as they are commonly used. | 2311923f2289cb4dae7017ca52d3980efa4b315a | bar: P3
29 | 3.1 |  | Replace if by if and only if? |  | Accept | [6 empty] | 1 | 0 | 1 | Updated requirement. | 87e7d974a44c9b727a88c48c5c4edf8b25806ee9 | bar: P1
30 | 3.2 |  | Missing info: "if collision is imminent". Scoping to include only pedestrians on the collision course. |  | Accept | [6 empty] | 1 | 0 | 1 | Updated requirement. | f5207ce5f631fcd3921c64b6d911390dfcf25999 | bar: P1
31 | 3.2 |  | Put False negative and False positive in bold font. |  | Accept | [6 empty] | 1 | 0 | 1 | Changed to bold font. | cf737015cdd4f5135e8acfe07ef29a29167bbd9a | bar: P4
32 | 3.2 |  | Despite the title, this section does not introduce any requirements, just classifies hazards |  | Reject | [6 empty] | 1 | 0 | 1 | We keep the section title to match AMLAS. | bar: P2
33 | 3.3 |  | Need more traceability here: how was SYS-ML-REQ2 derived? How is it connected to SYS-SAF-REQ1. Improve connection from high-level to low-level requirements. |  | Accept | [6 empty] | 1 | 0 | 1 | Improved traceability. | 006527578215e860f780aed7399f461782eb3022 | bar: P1
34 | SYS-ML-REQ1 |  | I would reformulate to “The pedestrian recog system shall detect pedestrian in all scenarios when the radar system reports below 4s to the collision” |  | Partial accept | [6 empty] | 1 | 0 | 1 | Updated the requirement in line with the comment. | bd40c25875fc3f7c027f8a268f47e08fd35b4144 | bar: P2
35 | 3.3 |  | SYS-ML-REQ1 and SYS-PER-REQ1 lead to inconsistencies due to time and space. |  | Accept | [6 empty] | 1 | 0 | 1 | Inconsistensies removed by specifying the performance requirements. | 6fdd73d419f21d8ee5e19d6ded540c3a8fc680fc | bar: P3
36 | 3.3.1 |  | Consistency: Align decimals/percentages and 1 out of 5. |  | Accept | [6 empty] | 0 | 1 | 1 | Aligned percentages and meters. | ede31c5a82d353e31b6bd645df53e3a040382396 | bar: P3 to P4
37 | SYS-PER-REQ4 |  | Add framerate and that the frames are concesuctive. |  | Accept | [6 empty] | 1 | 0 | 1 | Added FPS and consecutiveness. | 7760140ae988a9105896b5806adb4225fa72076b | bar: P1
38 | 3.3 |  | Align verbs. Detect, identify, recognize. |  | Accept | [6 empty] | 1 | 0 | 1 | Aligned verbs and explained the terms in Sec 2.1. | f30e2ec2226f91dff0c1b3211e0874e07ccd3693 | bar: P3
39 | 15. SYS-PER-REQ6 |  | Target platform undefined previously, unless you talk prosivic. Clarify what is included in “pedestrian recognition component”? Based on the previous description I would assume image recognition + safety cage (SYS-ML-REQ2) would be relevant for this req, right? |  | Partial accept | [6 empty] | 1 | 0 | 1 | Replaced target platform with Pro-SiVIC. Defined pedestrian recognition component in the system architecture description. | 848322646c1c2fb59bdcec94beeee1de5dde19a5 | bar: P2
40 | SYS-PER-REQ1-3 |  | SYS-PER-REQ1-3 and SYS-PER-REQ4 are confusing combined. Do 1-3 talk about frames or some “situations” or cases? Cause if you miss 20% of pedestrians you cannot assure max 7% false negative rate. I guess that 50m is a keyword here, but then REQ2 is more like further constraint on REQ5, that up 50m there is one rule, and 50-100 is another. |  | Partial accept | [6 empty] | 1 | 0 | 1 | Clarified requirements slightly. Additional requirements validation will follow downstream during system testing. | 7f3845145785acdeade555eb31b185cfc158bad4 | bar: P2
41 | SYS-PER-REQ1-2 |  | To me REQ2 is superfluous to req 1. Or did you mean “false positive” in REQ2, in which case it would not be. |  | Accept | [6 empty] | 1 | 0 | 1 | Updated the requirement. | 98f0ae64e5c8c5536f3f3eca0bf5afed644a0467 | bar: P2
42 | SYS-ROB-REQ2 |  | May address all possible variations, where pose is one of those. Other examples are size and appearance. Should we define that the entire body of pedestrian is captured in the FoV of camera? |  | Accept | [6 empty] | 0 | 1 | 1 | Added size and appearance as two new requirements. Clarified the expectation on the field of view. | 884af8981b9155cfc85420c4204c4449af6c37f9 | bar: P1; P4
43 | SYS-ROB-REQ2 |  | Are only upright positions covered? Or would a sitting pedestrian be ok? Clarify whether all poses count. |  | Accept | [6 empty] | 1 | 0 | 1 | Added an upright constraint to the requirement. Sitting and lying people are now excluded. | 337b1d08d7dac622f0c6d0a376c52661af7327de | bar: P2
44 | 3 |  | Introduce different quality levels for different relative speeds? |  | Reject | [6 empty] | 1 | 0 | 1 | We keep the requirements as they are for now. This might be considered as we further validate the requirements during system testing. | bar: P1
45 | 4.1 |  | Align language country road rural road |  | Accept | [6 empty] | 1 | 0 | 1 | Added "rural areas" in Sec 1.1. No change to the table in Sec 4.1 as that comes from NHSTA. | 0a13be76923b9c8fad58b548788ec2df1f716eb1 | bar: P6
46 | 4.3 |  | Pedestrian size range? I mean the 80cm kid and 2m adult look kind of different 100m away. I know there is something about that in data management, but ROB-REQ2 is closely related, so what defines the document placement? |  | Reject | [6 empty] | 1 | 0 | 1 | All sizes now count. This was adressed by comment 42. | bar: P2
47 | 4.5 |  | Clarify what calm winds mean. |  | Accept | [6 empty] | 1 | 0 | 1 | Updated based on definition in avaiation. | 95b375de8dbe26de3764380ebe3163bd6c76ca3f | bar: P2
28 | [11 empty] | 0 | 1 | 0
29 | [11 empty] | 0 | 1 | 0
30 | [11 empty] | 0 | 1 | 0
31 | [11 empty] | 0 | 1 | 0
32 | [11 empty] | 0 | 1 | 0
33 | [11 empty] | 0 | 1 | 0
34 | [11 empty] | 0 | 1 | 0
35 | [11 empty] | 0 | 1 | 0
36 | [11 empty] | 0 | 1 | 0
37 | [11 empty] | 0 | 1 | 0
38 | [11 empty] | 0 | 1 | 0
39 | [11 empty] | 0 | 1 | 0
40 | [11 empty] | 0 | 1 | 0
41 | [11 empty] | 0 | 1 | 0
42 | [11 empty] | 0 | 1 | 0
43 | [11 empty] | 0 | 1 | 0
44 | [11 empty] | 0 | 1 | 0
45 | [11 empty] | 0 | 1 | 0
46 | [11 empty] | 0 | 1 | 0
47 | [11 empty] | 0 | 1 | 0
48 | [11 empty] | 0 | 1 | 0
49 | [11 empty] | 0 | 1 | 0
50 | [11 empty] | 0 | 1 | 0
51 | [11 empty] | 0 | 1 | 0
52 | [11 empty] | 0 | 1 | 0
53 | [11 empty] | 0 | 1 | 0
54 | [11 empty] | 0 | 1 | 0
55 | [11 empty] | 0 | 1 | 0
56 | [11 empty] | 0 | 1 | 0
57 | [11 empty] | 0 | 1 | 0
58 | [11 empty] | 0 | 1 | 0
59 | [11 empty] | 0 | 1 | 0
60 | [11 empty] | 0 | 1 | 0
61 | [11 empty] | 0 | 1 | 0
62 | [11 empty] | 0 | 1 | 0
63 | [11 empty] | 0 | 1 | 0
64 | [11 empty] | 0 | 1 | 0
65 | [11 empty] | 0 | 1 | 0
66 | [11 empty] | 0 | 1 | 0
67 | [11 empty] | 0 | 1 | 0
68 | [11 empty] | 0 | 1 | 0
69 | [11 empty] | 0 | 1 | 0
70 | [11 empty] | 0 | 1 | 0
71 | [11 empty] | 0 | 1 | 0
72 | [11 empty] | 0 | 1 | 0
73 | [11 empty] | 0 | 1 | 0
74 | [11 empty] | 0 | 1 | 0
75 | [11 empty] | 0 | 1 | 0
76 | [11 empty] | 0 | 1 | 0
77 | [11 empty] | 0 | 1 | 0
78 | [11 empty] | 0 | 1 | 0
79 | [11 empty] | 0 | 1 | 0
80 | [11 empty] | 0 | 1 | 0
81 | [11 empty] | 0 | 1 | 0
82 | [11 empty] | 0 | 1 | 0
83 | [11 empty] | 0 | 1 | 0
84 | [11 empty] | 0 | 1 | 0
85 | [11 empty] | 0 | 1 | 0
86 | [11 empty] | 0 | 1 | 0
87 | [11 empty] | 0 | 1 | 0
88 | [11 empty] | 0 | 1 | 0
89 | [11 empty] | 0 | 1 | 0
90 | [11 empty] | 0 | 1 | 0
91 | [11 empty] | 0 | 1 | 0
92 | [11 empty] | 0 | 1 | 0
93 | [11 empty] | 0 | 1 | 0
94 | [11 empty] | 0 | 1 | 0
95 | [11 empty] | 0 | 1 | 0
96 | [11 empty] | 0 | 1 | 0
97 | [11 empty] | 0 | 1 | 0
98 | [11 empty] | 0 | 1 | 0
99 | [11 empty] | 0 | 1 | 0

## Capture-Recapture Estimates
Total Found by All Reviewers | 47
Estimated Not Yet Found | 159
Group Review Yield % | 22.82%
| P1 | P2 | P3 | P4 | P5 | P6
My Total Found | 13 | 19 | 13 | 10 | 2 | 2
My Unique | 10 | 17 | 6 | 3 | 1 | 1
Found in Common with Others | 3 | 2 | 7 | 7 | 1 | 1
Found by Others | 37 | 30 | 41 | 44 | 46 | 46
(Estimated Total Defects) | 132 | 206 | 73 | 61 | 70 | 70
Personal Review Yield % | 6.311% | 9.223% | 6.311% | 4.854% | 0.9709% | 0.9709%
Estimated Total Defects (only the value from column with most uniques is valid) | 22.82% P1: 206
(C) Bernie Thompson 2007 Creative Commons Attribution-Share Alike 3.0 License (free for commercial use with attribution, improvements to the sheet should be shared with the world). See http://leansoftwareengineering.com/capture-recapture-inspection/ for documentation, updated versions, and for comment areas to let everyone know about your questions, problems, interesting uses, and improvements